## Feng Yi
Week | Week Start Date | Week End Date | Task Performed | Hours Spent | Links to Proof of Work
1 | 8 May | 14 May | Initialize Repository | 0 | https://github.com/77chenchen/Orbital_Artemis_ArMap_Nus/issues/1
1 | 8 May | 14 May | Added login page with proper security features | 3 | https://github.com/77chenchen/Orbital_Artemis_ArMap_Nus/tree/feature-login
2 | 15 May | 21 May | Added OSM raster map tiles for ArMap campus map | 5 | https://github.com/77chenchen/Orbital_Artemis_ArMap_Nus/commit/1c2a1ad
3 | 22 May | 28 May | Set up OpenRouteService routing and geocoding research | 5 | https://github.com/77chenchen/Orbital_Artemis_ArMap_Nus/commit/f25e512
4 | 29 May | 4 Jun | Added UI for location search and campus result selection | 3 | https://github.com/77chenchen/Orbital_Artemis_ArMap_Nus/commit/83d7b41
2 | 15 May | 21 May | Researched MapLibre, OSM tile usage, and campus facility data structure | 3 | https://github.com/77chenchen/Orbital_Artemis_ArMap_Nus/commit/c3e9f67
3 | 22 May | 28 May | Built route tracing prototype and evaluated web-based routing limits before AR | 4 | https://github.com/77chenchen/Orbital_Artemis_ArMap_Nus/commit/f25e512
4 | 29 May | 4 Jun | Debugged search-location and map integration after branch merge | 3 | https://github.com/77chenchen/Orbital_Artemis_ArMap_Nus/commit/ebc1a5c
5 | 5 Jun | 11 Jun | Tested GPS marker behavior and map interaction on mobile layout | 3 | https://github.com/77chenchen/Orbital_Artemis_ArMap_Nus/commit/4dbf016
5 | 5 Jun | 11 Jun | Reviewed Raj feedback and discussed README feature rationale with team | 2 | https://github.com/77chenchen/Orbital_Artemis_ArMap_Nus/blob/main/README.md
5 | 5 Jun | 11 Jun | Updated project management evidence, milestone notes, and log coverage plan | 2 | https://github.com/77chenchen/Orbital_Artemis_ArMap_Nus/projects

## Wang QiChen
Week | Week Start Date | Week End Date | Task Performed | Hours Spent | Links to Proof of Work
1 | 11 May | 17 May | Initialize repository and shared full-stack project structure | 1 | https://github.com/77chenchen/Orbital_Artemis_ArMap_Nus/issues/1
1 | 11 May | 17 May | Built Atlas campus demo stack | 6 | https://github.com/77chenchen/Orbital_Artemis_ArMap_Nus/commit/5df7ad41f25e4ac8d079f4054d889703092ab394
1 | 11 May | 17 May | Configured shared API base and frontend-backend request routing | 3 | https://github.com/77chenchen/Orbital_Artemis_ArMap_Nus/commit/a14ec69f7889316cc6e32ec2691b3c7f7ffd082c
1 | 11 May | 17 May | Debugged login route handling and local environment setup | 2 | https://github.com/77chenchen/Orbital_Artemis_ArMap_Nus/commit/d6b8dd3
1 | 11 May | 17 May | Prepared Render deployment workflow and environment documentation | 3 | https://github.com/77chenchen/Orbital_Artemis_ArMap_Nus/commit/e0403ebcba666f529bd0202517884efc4c3a28f5
1 | 11 May | 17 May | Generated poster assets and checked submission packaging | 3 | https://github.com/77chenchen/Orbital_Artemis_ArMap_Nus/commit/d543ecb
2 | 18 May | 24 May | Rewrote frontend into responsive React Native Web layout | 4 | https://github.com/77chenchen/Orbital_Artemis_ArMap_Nus/commit/9872328caf25845727bbde7e30c11f1919d3459f
2 | 18 May | 24 May | Polished dashboard UI and campus assistant screens | 4 | https://github.com/77chenchen/Orbital_Artemis_ArMap_Nus/commit/c1ca5e79700e50815f13cc7c4a6f340f6b4ac8ab
2 | 18 May | 24 May | Added Google Sign-In integration and token handoff | 4 | https://github.com/77chenchen/Orbital_Artemis_ArMap_Nus/commit/b1ca50500392ab0491f03b752665b550fb4c9e59
2 | 18 May | 24 May | Researched OAuth/JWT session handling for protected dashboard routes | 3 | https://github.com/77chenchen/Orbital_Artemis_ArMap_Nus/commit/b1ca50500392ab0491f03b752665b550fb4c9e59
2 | 18 May | 24 May | Added iOS shell and validated mobile build path | 3 | https://github.com/77chenchen/Orbital_Artemis_ArMap_Nus/commit/befc3702705af4bd6aa31f361319ee1d7c118e52
3 | 25 May | 31 May | Manual testing for login routing, dashboard screens, and mobile responsiveness | 3 | https://github.com/77chenchen/Orbital_Artemis_ArMap_Nus/blob/main/README.md
3 | 25 May | 31 May | Validated Docker and Render deployment assumptions for MS1 demo readiness | 2 | https://github.com/77chenchen/Orbital_Artemis_ArMap_Nus/blob/main/deploy/README.md
3 | 25 May | 31 May | Drafted architecture, deployment, and testing explanation sections for MS1 submission | 4 | Submitted on Skylab
3 | 25 May | 31 May | Collected screenshots and verified project evidence links for MS1 documentation | 2 | Submitted on Skylab
End of MS1